## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Tester | 2025-11-24 | Signal Detection Fluctuation: The color analysis (HSV thresholding) occasionally fails to consistently register the RED light as 'ON' due to video compression artifacts or shifting light intensity. This results in missed "Signal Jumping" violations. | Sprint 1 | CV Engineer | Functional/Robustness | Analyzed color sensitivity; increased red_pct_threshold to 0.07 to tolerate slight dimming. | 2025-11-25 | Closed | Fixed threshold, pending regression test on varying lighting conditions.
2 | Dev Lead | 2025-11-23 | Output Video Playback Issue: The final output video (`output_speed_detection.mp4`) does not play in the Streamlit UI, causing a "Video not found" or "Corrupt file" error. This was due to codec incompatibility (XVID in an MP4 container). | Sprint 1 | Deployment | Performance/Environment | Updated `traffic_processor.py` to use `cv2.VideoWriter_fourcc(*"mp4v")` for native MP4/H.264 compatibility across all video writing stages. | 2025-11-25 | Closed | Verified successful playback in Streamlit and standard browsers.
3 | QA Tester | 2025-11-25 | False Wrong Way Trigger: Vehicles accelerating quickly or performing slight lane changes near the perspective vanishing point sometimes trigger a false `Wrong Way` violation. | Sprint 1 | CV Engineer | False Positive | Increased `MIN_TOTAL_DISTANCE_M` from 20 to 30 meters to require a longer, more sustained opposite movement before logging the violation. | 2025-11-25 | Open | Still monitoring the false positive rate on high-speed footage.
4 | Streamlit User | 2025-11-24 | Log Data Refresh Issue: The Violation Log DataFrame at the bottom of the Streamlit page did not update immediately after clicking 'Process Video'. | Sprint 1 | UI/Frontend | UI/Integration | Implemented `st.session_state` update after successful processing to ensure the Streamlit UI refreshes with the new CSV data immediately. | 2025-11-26 | Closed | Confirmed instant log update upon completion button press.
5 | QA Tester | 2025-11-25 | Overlapping Violations: If a vehicle commits two violations (e.g., speeding and signal jumping) in the same frame, the script only logged the first violation it checked, leading to incomplete reporting. | Sprint 1 | CV Engineer | Logic/Reporting | Refactored violation tracking dictionaries to check and log all possible violation types independently within the tracking loop. | 2025-11-26 | Open | Code reviewed, pending end-to-end integration test with simultaneous violations.
6 | Performance Tester | 2025-11-26 | Processing Latency: The overall video processing time is too long (average 15s for 10s video) when run locally, impacting user experience. | Sprint 2 | ML Ops | Performance | Investigating options: Reducing frame skip logic, optimizing YOLO settings, or utilizing lighter models (e.g., YOLOv8-nano-quantized). | 2025-11-27 | Open | Targeting 5s processing time for 10s video.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others